## Slide 1: HappyHour Co. Company Profile
  Producer and marketer of beer, spirits and non-alcoholic beverages
  Headquarter in Singapore with operations in Malaysia and China; manufacturing outsourced to Brew Co. in Malaysia
  Distribution and direct sales across all markets
  #1 player in beer and spirits in Singapore and Malaysia; #1 in non-alcoholic beverages in Malaysia
  High end product offerings in spirits segment (vodka, tequila) commanding premium valuation
  Growth strategy: recently expanded into China; new bottling facilities planned for Cambodia
  Founded in 1975 by Ms. Happy
Overview
Shareholders
Indicative valuation
Source: Company website; Broker industry reports; News articles
Key financials
1
Leading producer and marketer of beer and spirits in Singapore and Malaysia with growing operations in the region

## Slide 2: Overview of auction process and key workstreams
1
 | Date | Event | Key workstreams
Round 1: Indicative Bid Phase | Mar 19, 2020 | Commencement of Indicative Bid Phase Release of Indicative Bid Documents | Due Diligence Conduct initial due diligence based on the Indicative Bid Documents Maintain Q&A log Valuation Conduct initial valuation based on the Indicative Bid Documents Structure and Financing Confirm buyer entity and any co-investor involvement Confirm preliminary financing approach Approvals Identify any internal or regulatory approvals required
 | From 9am Apr, 9 2020 to 5pm Apr 13, 2020 (HKT) | Lodgment of Indicative Bid Questions | 
 | By 5pm May 13, 2020 (HKT) | Indicative Bid deadline | 
Round 2: Final Bid Phase | Late May 2020 | Commencement of Final Bid Phase Release of Process Letter Two | Site Visits & Management Presentation Arrange site visit and management presentation Prepare follow-up questions for management Due Diligence Continue to conduct due diligence using additional information provided in data room Update and maintain Q&A log Valuation Refine valuation analysis based on financial forecast provided Financing Confirm financing sources Approvals Begin preparation of internal and regulatory approval materials
 | Late Jul 2020 | Final Bids due |